## Sheet1
Schedule Model
| Week 1 (Jan 20-27) |  |  |  | Week 2 (Jan 27- Feb 3rd)
| Task |  |  | Done | Task | Done
| Warrior Animations |  |  | Yes | Implement Warrior Class
| Basic UI |  |  | Yes | Change Warrior Class to intended design and start Mage animations
| Basic Map |  |  | TBC | Detailed UI Navigations and Microtransaction
| Warrior Sounds |  |  | Halfway done | Finish Warrior Sounds
| Basic Objective |  |  | Yes | Scoring System
| Class Designs |  |  | Yes
Journal
| Week | Duration | Content
| Jan 20-27 | 2 Meetings - 30 mins | This weeks meeting we talked about who's doing what. Zyrynyl is doing warrior animations, William is doing basic objective, Patryk is doing the warrior sounds, Niall is doing the basic menu gui, Euan is doing the basic map and finally Thomas is doing the warrior design. After doing this we started brainstorming on what the game will be and what the basic game will have. And we will make sure that were working with the kanban board.
| Jan 27-Feb 3rd | 1 Meeting - 30 mins | This weeks meeting we talked about improving the PMIS stuff and also talked about what the game will have, eg (microtransaction, models and the core gameplay). We also got a lot more information about of what has to be in the game.