## Sheet1
Schedule Model
| Week 1 (Jan 20-27) |  |  |  | Week 2 (Jan 27- Feb 3rd) | [11 empty] | Week 3 (Feb 3rd- Feb 10th)
| Task |  |  | Done | Task | [8 empty] | Done |  |  | Task | Done
| Warrior Animations |  |  | Yes | Implement Warrior Class | [8 empty] | Halfway Done |  |  | Finish Implementing
| Basic UI |  |  | Yes | Change Warrior Class to intended design and start Mage animations | [8 empty] | Done |  |  | Alchemist Animations
| Basic Map |  |  | TBC | Detailed UI Navigations and Microtransaction | [8 empty] | Halfway Done |  |  | In game Microtransaction
| Warrior Sounds |  |  | Halfway done | Finish Warrior Sounds | [8 empty] | Done |  |  | Mage Sounds
| Basic Objective |  |  | Yes | Scoring System | [8 empty] | Nearly Done |  |  | Scoring System
| Class Designs |  |  | Yes | Map | [8 empty] | Done |  |  | Character Models
| Tasks that must be done |  |  |  | The Roblox Project - Milestone Schedule
| Task |  |  | Done | Task | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11
| Animations for the 3 classes |  |  |  | Playable Basic Game |  |  |  | ♦
| Microtransaction integrated |  |  |  | Mock up Monetisation |  |  |  |  | ♦
| Map |  |  |  | Main 3 classes Implemented | [5 empty] | ♦
| Objectives |  |  |  | 1st Map |  |  |  | ♦
| Sounds for the classes |  |  |  | Models | [8 empty] | ♦
| Functioning UI and HUD |  |  |  | Game Mechanics | [6 empty] | ♦
| Weapons/Gear that can be bought |  |  |  | Fully Implemented Microtransaction | [9 empty] | ♦
[5 empty] | Finished Game | [10 empty] | ♦
Journal
| Week | Duration | Content
| Jan 20-27 | 2 Meetings - 30 mins | This weeks meeting we talked about who's doing what. Zyrynyl is doing warrior animations, William is doing basic objective, Patryk is doing the warrior sounds, Niall is doing the basic menu gui, Euan is doing the basic map and finally Thomas is doing the warrior design. After doing this we started brainstorming on what the game will be and what the basic game will have. And we will make sure that were working with the kanban board.
| Jan 27-Feb 3rd | 2 Meetings - 30 mins | This weeks meeting we talked about improving the PMIS stuff and also talked about what the game will have, eg (microtransaction, models and the core gameplay). We also got a lot more information about of what has to be in the game, e.g. customizable weapons and looks for the microtransaction and also has to fit the setting on where the players will play.
| Feb 3rd-Feb 10th | 1 Meeting