## RICs
ID | Description | Type | Date Identified | Impact | Probability | Importance | Response | Owner | Closure Date
1 | Reliant on everyone making the deadline | Risk | 2020-01-20 |  | Low | 0 | Have weekly meetings to make sure everyone is doing work
2 | Team members not doing any work | Risk | 2020-01-20 |  | Medium | 0 | Talk to them as soon as possible
3 | Team members learning a new software to make games on | Risk | 2020-01-20 |  | Medium | 0 | Look at tutorials to make it easier
4 | Having issues on everyone working on one game | Issue | 2020-01-20 |  |  | 0 | We made a teamcreate in roblox which makes the group simultaneously able to work on the project.
5 | Having learn a new language script | Issue | 2020-02-06 |  |  | 0 | Might delay our deadlines